## Foglio1
Deliverable | Date | Responsible | Title | Status
D5.1 | 3 | Caen | Definition of internal architecture and interface between software modules | Sapienza version
D5.2 | 3 | Caen | Definition of the use cases for the demonstrations | Draft
D5.3 | 12 | Sapienza | Technical specification of the robot set-up and of the communication infrastructure
D5.4 | 15 | Caen | Description of the first demonstration
D0.1 | 18 | Caen | Document describing the mid-term assessment
D1.1 | 18 | Sapienza | Knowledge-based environment modelling | Draft
D1.2 | 18 | Sapienza | Software component for environment modelling
D2.1 | 18 | VUB | Description and specification of the proposed solutions for the sensor processing
D2.2 | 18 | VUB | A software of sensor, image and video processing
D1.3 | 21 | Sabanci | Methods for integrating spatial reasoning with common sense reasoning and non-monotonic reasoning
D1.4 | 21 | Sabanci | Software component for knowledge base reasoning
D2.3 | 21 | VUB | Description and specification of the proposed solutions for the scene analysis
D2.4 | 21 | VUB | A software of scene analysis
D4.1 | 24 | Sapienza | Document of specification of localisation and navigation methods
D4.2 | 24 | Sapienza | A software of navigation module to integrate in the whole architecture
D3.1.1 | 27 | Sapienza | Multi-modal human-robot interaction
D3.1.2 | 27 | Caen | Human needs estimation
D3.2.1 | 27 | Sapienza | Developed software for multi-modal human-robot interaction
D3.2.2 | 27 | Caen | Developed software for human needs estimation
D4.3 | 30 | Caen | Document of specification of multi-robot planning using DEC-POMDP | Draft
D4.4 | 30 | Caen | A software of decision module to integrate in the whole architecture
D5.5 | 33 | Caen | Description of the final demonstration
D0.2 | 36 | Caen | Document describing the final assessment
D5.6 | 36 | Sapienza | Performance evaluation in the uses cases of the final demonstration